## Construction Activities
Activity | Description | Predecessors | Duration (days)
A | Clear site | - | 1
B | Bring utilities to site | - | 2
C | Excavate | A | 1
D | Pour foundation | C | 2
E | Outside plumbing | B, C | 6
F | Frame house | D | 10
G | Do electric wiring | F | 3
H | Lay floor | G | 1
I | Lay roof | F | 1
J | Inside plumbing | E, H | 5
K | Shingling | I | 2
L | Outside sheathing insulation | F, J | 1
M | Install windows and outside doors | F | 2
N | Do brick work | L, M | 4
O | Insulate walls and ceiling | G, J | 2
P | Cover walls and ceiling | O | 2
Q | Insulate roof | I, P | 1
R | Finish interior | P | 7
S | Finish exterior | I, N | 7
T | Landscape | S | 3

## example
job | predecessors | time
A | - | 10
B | - | 12
C | A,B | 15
D | B | 18
E | B | 16
F | C | 11
G | D,E | 10
H | F,G | 8